**TECHNICAL EDUCATION QUALITY IMPROVEMENT PROGRAMME (PHASE - III)**

**Equity Action Plan Jan 2020 to Sept 2020**

**Name of Institute: National Institute of Technology Raipur**

**Part A: For soft activities**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Activity**  | **Action to be taken** | **Coordinator from the institute** | **Executing agency** | **Date & duration**  | **Frequency**  | **Whether continuing from last action plan or new activity** | **Indicator to measure outcome (should be quantifiable)** | **Estimated Expenditure**  |
|  | To identify weaknesses in all students and take remedial action | Weakness identified from the Mid Semester Examination and Teachers Assessment Report. Remedial Classes | Dr. S P Mahapatra &Dr. Ayush Khare | NIT Raipur  | 20/01/2020 onwards(10 weeks per sem) | One class (60 Mins) per week per subject | Continuous | Pass percentage in end semester and supplementary examinations. | Rs. 1.50 Lakhs (Expected from TEQIP Fund) |
|  | To improve language competency, soft skills and confidence levels. | It is a part of the curriculum for improvement of the students.In addition to that, efforts are being made to provide employability skill training from external agency. | 1. HOD (Humanities)2. Dr. S K Mukti | HSS Department and CDC, NIT Raipur  | 06/01/02020 onwards (Semester wise as per Academic calendar)(3 months) | Routine work | Continuous | Pass percentage in end sem examinations. | Rs. 11.00 Lakhs(From TEQIP Fund) |
|  | To provide special skills training to students with priority to the weak students. | Guest lectures by eminent experts from reputed organizations, workshops / training programs conduction by different departments and also by CD Cell, NIT Raipur. | 1. Dr. S K Mukti2. Dept. TEQIP Coordinators / Prof. I/C | Concerned Departments and CD Cell and Clubs, NIT Raipur | Semester wise as per Academic calendar | Regular | Continuous | Data of placed students in industries/ in Higher studies. | Rs. 1.00 Lakh(Expected from TEQIP and Institute Fund) |
|  | Training of teachers in subject matter and pedagogy, particularly to improve the performance of weak students | Domain training on the basis of need / link up with industry to keep abreast of cutting edge technology. | Dean (FW) | Institutes of higher learning |  Semester wise | Based on the requirement of faculty members | Continuous | No of Teachers trained in an academic year. | Rs. 2.00 lakhs (Expected from Institute Fund) |
|  | Make campuses physically and socially gender-friendly; especially provide adequate and suitable facilities to women students and faculty | Sanitary napkin vending machines have been fitted in various places in institute building as well as in girls hostels.  | Dean (FW)Dean (SW) | NIT Raipur | Within a month(One time activity) | Based on the need | Continuous | Satisfaction survey from stake holders (Girls, women faculty and staff). | No Requirement of Fund |
|  | Hold innovation and Knowledge Sharing Workshops yearly to improve knowledge sharing | Workshops and Guest lecturers to share the knowledge. | Dr. R N PatelandDr. Saurabh Gupta | Startup and Innovation Cell of NIT Raipur  | Semester wise | Half Yearly | Continuous | Feedback from stake holders. | Rs. 5.00 Lakhs (Expected from Teqip Fund) |
|  | Sharing information and knowledge about engineering courses and institution | Awareness lectures, talks in nearby schools and villages.Visit of school students to Technical events (like Avartan) | Dr. U K DewanganDr. S Bhowmick  | * Prof. I/C Unnath Bharat Abhyan &
* Prof. I/C Technical Events

NIT Raipur | Approx. 10 activities per semester | * Half Yearly
* Yearly
 | Continuous | * No. of schools visited and photographs
* Feedback of stake holders
 | Rs. 1.00 lakh (Expected from Institute Fund) |
|  | Provide appropriate infrastructure for physically challenged students  | Most of the institute premises have ramps, lifts, toilets and hostel facilities for physically challenged persons and are in progress. | Shri Suraj Pratap Shrivastava | Estate office,NIT Raipur  | Continuous | Throughout the year | Continuous | Satisfaction survey from stake holders. | No Requirement of Fund |
|  | Special efforts for training / internship placement of weak students | Placement for summer internship of weak students. | Dept. Prof. I/C T&PProf. I/C T&P | Dept. Training Coordinator and CDC cell | Sem wise | Yearly | Continuous |  No of students trained. | No Requirement of Fund |
|  | A two tier grievanve redress mechanism (GRM) | Existing-“Samadhan cell and Departmental Grievance Committee (DGC)”. | Dr. Hina ChawdaHODs | Prof. I/C, Dept. of HSS &DGC of concerned department, NIT Raipur  | Continuous | Throughout the year | Continuous |  Minutes of DGC meetings and Report of Smadhan Cell | No Requirement of Fund |
|  | Ensure that institutional mechanisms to protect and address the needs and concerns of women students are established.  | Women Grievance Cell is established. | Prof. I/C, Women Grievance Cell, NIT Raipur | Prof. I/C, Women Grievance Cell, NIT Raipur | Continuous | Throughout the year | Continuous |  No of complaints resolved | No Requirement of Fund |
|  | Develop a standard model for tracking of student progress\* | Result analysis | HODs | Departmental Academic Committee NIT Raipur | Sem Wise | Half Yearly  | Continuous |  Related Departmental Academic Committee and related minutes of senate | No Requirement of Fund |
|  | Peer Learning Groups of students  | Learning through discussion among students | Prof I/c SAHAYOG club NIT Raipur | Prof I/c SAHAYOG club NIT Raipur  | Continuous | Throughout the year | Continuous |  Reports of Prof I/c | No Requirement of Fund |
|  | Appointing Mentors for Students | Assigning faculty member as a mentor for 20 students  | Dean AcademicsNIT Raipur | Dean AcademicsNIT Raipur  | Continuous | Throughout the year | Continuous |  Mentor Reports | No Requirement of Fund |

**Part B: For Minor Civil works:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Activity**  | **Coordinator from the institute** | **Executing agency** | **Date & duration**  | **Indicator to measure outcome**  | **Estimated Expenditure**  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

Note:

1. For suggestive activity please refer column 1 of table of details of Equity Action plan in section 8 of Project Implementation Plan(PIP)
2. If the activities are being carried out by the outside agency, mention name of the agency